## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: | [6 empty] | INSTUTUTE & DEPARTMENT NAME: | [11 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: | [6 empty] | DATE: | [11 empty] | 2024-10-07
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Radhika Pradhan,Gauri Salvi, Tejas Patil, Chinmay Pawaskar | 2024-07-10 | 2024-07-24 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Radhika Pradhan,Gauri Salvi, Tejas Patil, Chinmay Pawaskar | 2024-07-24 | 2024-08-07 | 2 | 100% | bar: WEEK 3 M to WEEK 5 F
1.3 | Discussing the project topic with the help of paper prototype. | Radhika Pradhan,Gauri Salvi, Tejas Patil, Chinmay Pawaskar | 2024-08-07 | 2024-08-21 | 2 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Radhika Pradhan, Chinmay Pawaskar | 2024-08-21 | 2024-09-10 | 3 | 100% | bar: WEEK 7 M to WEEK 9 F
1.5 | Presentation I | Radhika Pradhan,Gauri Salvi, Tejas Patil, Chinmay Pawaskar | 2024-09-10 | 2024-09-18 | 1 | 100% | bar: WEEK 10 M to WEEK 10 F
2 | Project Design and Implementation
2.1 | Database Design | Radhika Pradhan,Gauri Salvi, Tejas Patil | 2024-09-18 | 2024-09-25 | 1 | 100% | bar: WEEK 11 M to WEEK 12 F
2.2 | Database Connectivity of all modules | Radhika Pradhan, Tejas Patil | 2024-09-25 | 2024-10-02 | 1 | 100%
2.3 | Integration of all modules and Report Writing | Radhika Pradhan, Tejas Patil, Chinmay Pawaskar | 2024-10-02 | 2024-10-05 | 1 | 100% | bar: WEEK 12 M to WEEK 13 F
2.4 | Presentation II | Radhika Pradhan,Gauri Salvi, Tejas Patil, Chinmay Pawaskar | 2024-10-05 | 2024-10-07 | 1 | 100% | bar: WEEK 14 M to WEEK 14 F